## Progress_Review
Category | Status | Details
Completed Work | Complete | Week 1 governance foundation; Week 2 execution monitoring; Week 3 integration readiness assessment
Incomplete Work | Pending | Cross-track output validation (deferred to Week 4 per Week 3 policy)
Delayed Work | Minimal | No delays identified based on available evidence
Major Achievements | Complete | All PM deliverables completed on schedule across three weeks; risk register matured from 11 to 15 risks; evidence-based Integration Readiness Tracker introduced
Remaining Activities | Pending | Week 4: final testing, refinement, documentation, presentation

## Integration_Readiness
Track | Contributor | Main Week 3 Output | Evidence Type | Evidence Level | Integration Readiness | Outstanding Work
Data Analytics | Franklin | Direct message confirming Week 3 status: SQL analysis complete; Python analysis and Power BI expansion in progress | Direct message from contributor | Confirmed | Partially Ready (SQL outputs ready now; Python and dashboard pending) | Python analysis, Power BI dashboard, findings, recommendations
Data Analytics | Mohammed Rashid | Documentation file describing advanced SQL analysis, Python analytics, dashboard, validated findings and management recommendations | Shared documentation file from contributor | Confirmed | Partially Ready (documentation complete; formal integration confirmation pending) | Integration readiness confirmation, final dashboard polish
Data Science | Unotidashe Jacob Hove | Model validated; code pushed to GitHub | Public LinkedIn post and public GitHub repository | Reviewed | Not Confirmed | Integration readiness not explicitly stated; Week 4 validation pending
ML Engineering | Zaid HARBOUL | Reported completion with integration reference | Public LinkedIn post | Reported | Reported Integration-Ready (self-stated) | Independent validation pending
ML Engineering (alternative) | Charlez023 | Full Week 3 repository: code, 20 tests, FastAPI /predict endpoint | Public GitHub repository | Reviewed | Not Confirmed | End-to-end validation pending per repository README
Generative AI | No contributor identified | Not available | No source available | Not Confirmed | Not Confirmed | All information
Project Management | Lamiaa SAMRAOUI (self) | All Week 3 PM deliverables | This submission | Confirmed | Ready | Final documentation and presentation in Week 4

## Risk_Register
ID | Risk | Probability | Impact | Rationale | Mitigation | Owner | Week 3 Status
R-01 | Data-quality issues | Medium | Medium |  | Data-profiling pass | DA and DS | Resolved
R-02 | Track schedule slippage | Medium | High |  | Weekly tracking | PM | Changed
R-03 | Dependency communication | Medium | Medium |  | Weekly register review | PM | Resolved
R-04 | Predictive model limited by target imbalance | Medium | High |  | Realistic expectations documented | DS | Active
R-05 | GenAI hallucination | Medium | High |  | No-invented-policy rule | GenAI | Active
R-06 | Scope creep | Low | Medium |  | Reinforce governance | PM | Resolved
R-07 | Tool access | Low | Medium |  | Confirm access | Individual and PM | Resolved
R-08 | Limited buffer | Medium | High |  | Timeline milestones | PM | Active
R-09 | Integration fails due to incompatible outputs | Medium | High |  | Flag format expectations | PM and MLE | Changed
R-10 | Inconsistent documentation | Low | Medium |  | Share template | PM | Resolved
R-11 | Unclear acceptance criteria | Medium | High |  | Define evidence early | PM | Changed
R-12 | DA to DS hand-off timing | Medium | High |  | Confirm hand-off | PM | Resolved
R-13 | GenAI grounding failures | High | High |  | Refine prompts and re-test | GenAI | Active
R-14 | Week 4 time compression | High | High | Week 4 requires five activities (testing, refinement, documentation, integration, presentation) in one week. Any Week 3 slip cascades directly into Week 4. | Prioritise Week 4 critical path; complete documentation in advance; use Days 1 and 2 for validation only | PM | New
R-15 | Cross-track integration readiness not confirmed for most tracks | High | Medium | Only Data Analytics has reached Confirmed evidence level. Data Science and ML Engineering are at Reported or Reviewed level. Generative AI has no evidence available. | Retain clear evidence labels; attempt confirmation in Week 4 where possible | PM | New

## Issue_Log
Issue | Impact | Priority | Action | Owner | Status
Cross-track integration readiness not confirmed for most tracks | Cannot fully validate integration until Week 4 | High | Retain evidence-level labels; attempt confirmation in Week 4 where possible | PM | Open
Generative AI Week 3 evidence not available | R-13 status cannot be updated | Medium | Monitor for any new GenAI public or direct update; note absence in Week 4 | PM | Open
Two ML Engineering sources exist | Ambiguity about which source represents the final MLE output | Low | Document both sources; note relationship is not confirmed | PM | Open
Multiple contributors per track | Different statuses may not align | Medium | Track each contributor separately in the tracker | PM | Accepted
Resolved Week 1 risks still carried in register | Register was carrying stale items | Low | Marked Resolved and moved to resolved list | PM | Resolved
Week 3 timeline required new readiness column | Prior format insufficient for integration phase | Low | Added Integration Readiness Tracker with evidence levels | PM | Resolved

## Decision_Log
Decision | Reason | Evidence | Impact | Date
Adopted four-level evidence hierarchy | Distinguish direct confirmation from public reporting and from reviewed public outputs | Week 3 brief permits use of available outputs | All cross-track statuses clearly labelled | Week 3, Day 1
Documented each contributor separately within each track | Multiple independent contributors per track | Direct communication, shared files, public posts, public repos | Tracker preserves per-contributor accuracy | Week 3, Day 1
Flagged Generative AI as Not Confirmed | No public or direct source found | No evidence available | GenAI remains unconfirmed for Week 4 | Week 3, Day 1
Added R-14 (Week 4 time compression) | Week 4 brief requires five activities in one week | Week 4 roadmap | Week 4 Readiness Plan prioritises critical path | Week 3, Day 3
Added R-15 (Integration readiness not confirmed for most tracks) | Only DA reached Confirmed level | Review of all cross-track evidence | Risk register reflects honest evidence position | Week 3, Day 3
Upgraded DA evidence level to Confirmed | Direct communication and shared documentation received | Franklin (message) and Mohammed Rashid (documentation file) | DA is the only cross-track item at Confirmed level | Week 3, Day 5
Did not attempt formal cross-track collaboration | Week 3 brief states individual responsibility; no collaboration expected | Week 3 brief | All cross-track evidence comes from available sources only | Week 3, Day 5
Updated R-01, R-03, R-06, R-07, R-10, R-12 to Resolved | No further issues; statuses confirmed by Week 3 review | Risk review against Week 3 brief | Removes six risks from active tracking | Week 3, Day 4

## Week4_Readiness_Plan
Day | Activity | Priority | Owner | Dependencies
Day 1 | Review any new evidence published after Week 3 | Critical | PM | None
Day 1 | If any track offers direct confirmation, document it | Critical | PM | None
Day 1 | Validate Week 3 assessments against any new information | Critical | PM | Day 1 actions above
Day 2 | Final risk register update with Week 4 statuses | Critical | PM | Day 1 validation
Day 2 | Final issue log update | Important | PM | Day 1 validation
Day 3 | Complete Week 4 documentation | Critical | PM | All registers finalised
Day 3 | Final timeline review and close-out | Important | PM | Day 2 updates
Day 4 | Prepare presentation outline | Critical | PM | Day 3 documentation
Day 4 | Draft 5 to 10 minute presentation | Important | PM | Day 4 outline
Day 5 | Record presentation | Critical | PM | Day 4 draft
Day 5 | Final submission to Drive | Critical | PM | Day 5 recording
Day 5 | Update GitHub repository | Important | PM | Day 5 recording
Day 6 (buffer) | Any final revisions | Important | PM | All
Day 7 (deadline) | Final submission confirmation | Critical | PM | All

## Evidence_Sources
Track | Contributor | Evidence Type | Evidence Description | Evidence Level | Source Link
Data Analytics | Franklin | Direct message from contributor | Message confirming Week 3 status: SQL complete and reconciled to Week 2 KPIs; Python and Power BI in progress; partially ready for integration | Confirmed | Not applicable (direct message)
Data Analytics | Mohammed Rashid | Shared documentation file | Documentation file describing advanced SQL, Python analytics (5+ visualizations), custom dashboard, 5 validated findings, 5 recommendations | Confirmed | Not applicable (shared file)
Data Science | Unotidashe Jacob Hove | Public LinkedIn post and public GitHub repository | Posts and repository ANALYSTLAB-JACOB-INTERNSHIP-FINTECHBANK showing validated model development and code | Reviewed | [insert LinkedIn and GitHub URLs]
ML Engineering | Zaid HARBOUL | Public LinkedIn post | Post reporting completion with reference to integration readiness (self-stated) | Reported | [insert LinkedIn post URL]
ML Engineering (alternative) | Charlez023 | Public GitHub repository | Repository FinTrust-ML-Engineering: features, model comparison, FastAPI /predict endpoint, 20 passing tests, ML pipeline | Reviewed | [insert GitHub URL]
Generative AI | No contributor identified | No source available | No public or direct Week 3 source found | Not Confirmed | Not applicable
Project Management | Lamiaa SAMRAOUI (self) | This submission | All Week 3 PM deliverables | Confirmed | https://github.com/LamSa1/FinTrust-PM-Portfolio