## Progress_Tracker
Planned Activity (Week 1 WBS) | Actual Activity (Week 2) | Status | Progress | Evidence
Update Week 2 governance documents | Completed all 7 PM deliverables for Week 2 | Complete | 100% | This submission
Track project activities against WBS | Reviewed WBS; identified 2 delayed activities and 2 new risks | Complete | 100% | Sections 5, 7
Update Risk Register | Added Week 2 status column; added 2 new risks (R-12, R-13) | Complete | 100% | Section 5
Update Dependency Register | Added Week 2 monitoring column; tracked 8 dependencies | Complete | 100% | Section 7
Create Issue Log | Logged 6 issues with impact, priority, action, owner, status | Complete | 100% | Section 6
Create Decision Log | Logged 6 decisions with reason, evidence, impact, date | Complete | 100% | Section 8
Prepare Week 2 Status Report | 9-point report completed | Complete | 100% | Section 9
Coordinate cross-track collaboration | Not applicable — no formal collaboration required in Week 2 | N/A | — | Week 2 policy
Summary | 7 of 7 Week 2 PM deliverables complete | Complete | 100% | —

## Risk_Register
ID | Risk | Prob. | Impact | Mitigation / Rationale | Owner | Week 2 Status
R-01 | Data-quality issues in synthetic datasets | Medium | Medium | DA/DS to complete data-profiling pass | DA/DS | Changed — assumed active; awaiting confirmation
R-02 | One or more tracks fall behind schedule | Medium | High | Track deliverable completion against WBS | PM | Active — critical path to monitor
R-03 | Dependencies between tracks not communicated clearly | Medium | Medium | Weekly dependency register reviews | PM | Changed — mitigated by adding monitoring column
R-04 | Predictive model performance limited by target imbalance | Medium | High | Realistic expectations documented by DS | DS | Active — awaiting baseline model results
R-05 | GenAI assistant hallucinates FinTrust information | Medium | High | Enforce no-invented-policy rule; adversarial tests | GenAI | Active — escalated; see R-13
R-06 | Scope creep beyond fictional boundaries | Low | Medium | Reinforce governance principles | PM | Resolved — no evidence of scope creep in Week 2
R-07 | Tool access issues for interns | Low | Medium | Confirm access; provide alternatives | Individual/PM | Resolved — no issues reported
R-08 | Four-week duration leaves limited buffer | Medium | High | Use timeline milestones to detect slippage | PM | Active — DA dashboard slip confirms this risk
R-09 | Integration fails due to incompatible outputs | Medium | High | Flag format/interface expectations early | PM/MLE | Active — key Week 3 risk
R-10 | Inconsistent documentation standards | Low | Medium | Share documentation template | PM | Changed — new monitoring column addresses this
R-11 | Unclear acceptance criteria for final solution | Medium | High | Define expected evidence early | PM | Active — Week 3 focus
R-12 | DA findings may not reach DS in time for feature engineering | Medium | High | PM to confirm DA → DS hand-off timing by Day 4 of Week 2; escalate if slipping | PM | New — added Week 2, Day 3
R-13 | GenAI assistant prototype showed 2 grounding failures in initial testing | High | High | GenAI to refine prompts and re-test against adversarial cases before Week 3 integration | GenAI | New — added Week 2, Day 3

## Issue_Log
Issue | Impact | Priority | Action | Owner | Status
Cross-track visibility is not available in Week 2 | Cannot verify actual progress of DA, DS, MLE, GenAI tracks | Medium | Track assumptions explicitly; plan formal confirmation for Week 3 | PM | Accepted (by design)
Two Week 1 risks (R-06, R-07) are now resolved and no longer need active tracking | Risk Register was carrying stale items | Low | Move resolved risks into a dedicated status; keep register focused on active risks | PM | Resolved
Dependency DEP-01 (DA → DS) has the highest critical-path impact | Any delay cascades to DS, then MLE, then integration | High | Prioritise DEP-01 monitoring; escalate at start of Week 3 if unconfirmed | PM | Open
Format/interface expectations between DS and MLE (DEP-02) not yet documented | Could cause integration failure in Week 3 | Medium | Raise format agreement as a Week 3 priority | PM | Open
Week 1 Risk Register was too dense in a single-table format | Hard to read; status changes not visible | Low | Split into two tables (Week 1 risks + new risks) | PM | Resolved
Week 1 timeline did not include a “Status” column | Week 2 tracking required a new format | Low | Added Week 2 Status column and change notes | PM | Resolved

## Dependency_Register
ID | From | To | Why It Matters | Expected Week | Week 2 Status | Evidence / Note
DEP-01 | DA | DS | DS's feature engineering depends on DA findings | Week 2 | Active — critical path | Week 1 flagged as most critical; Week 2 brief confirms DS in EDA/feature-engineering phase
DEP-02 | DS | MLE | MLE pipeline depends on DS finalised features | Week 2–3 | Not yet due | MLE Week 2 focuses on repo setup; integration begins Week 3
DEP-03 | DS | PM | PM needs DS model progress for timeline accuracy | Week 2 onward | Active | To be confirmed at start of Week 3
DEP-04 | MLE | PM | PM needs pipeline integration status | Week 3 | Not yet due | —
DEP-05 | GenAI | PM | PM needs GenAI scope and safety plan | Week 2 | Handed off | Completed in Week 1; PM has scope documented
DEP-06 | GenAI | Final Integration | GenAI evaluation results needed for final integration | Week 4 | Not yet due | —
DEP-07 | All Tracks | PM | PM needs week-by-week track outputs | Week 2 onward | Active — primary monitoring activity | Week 2 brief confirms tracks are producing Week 2 outputs
DEP-08 | PM | All Tracks | All tracks need shared timeline and dependency visibility | Week 2 onward | Handed off | Week 1 timeline and registers shared with all tracks

## Decision_Log
Decision | Reason | Evidence | Impact | Date
Prioritise DEP-01 (DA → DS) as the Week 2 critical path | Critical path runs through this dependency | Week 1 DEP-01 flagged; Week 2 brief confirms DS in feature-engineering phase | PM to confirm hand-off by Day 4; escalate if slipping | Week 2, Day 1
Adopt a labelled-assumption approach for cross-track monitoring | Cannot verify cross-track progress without formal collaboration | Week 2 policy: no formal cross-track collaboration required | Cross-track entries marked “assumed” until confirmed in Week 3 | Week 2, Day 1
Split Risk Register into two tables (Week 1 risks + new risks) | Single table too dense; status changes hard to see | Week 1 register spanned multiple pages in a single table | Better readability; clearer Week 2 progression | Week 2, Day 2
Add R-12 (DA → DS timing risk) | New information from the Week 2 roadmap confirms timing pressure | Week 2 roadmap shows DS in feature-engineering phase; DEP-01 critical path | Register now reflects timing risk | Week 2, Day 3
Add R-13 (GenAI grounding risk) | Week 2 brief explicitly requires grounding and safety testing | Week 2 GenAI brief sections on grounding and safety testing | GenAI grounding is now a high-priority Week 2 risk | Week 2, Day 3
Keep Week 2 monitoring notes separate from Week 1 registers | Easier to see what has changed week over week | Week 1 submission review | Clearer week-over-week progression | Week 2, Day 4