## Slide 1
ANALYSTLAB AFRICA
FinTrust Digital Bank
Week 2 Status Report — Summary Deck
Project Management Track | Analyse & Prepare
Lamiaa SAMRAOUI | Week 2 of 4 | [Insert Date]

## Slide 2
Project Health
Week 2 — Analyse & Prepare
🟡 AT RISK
7 of 7 PM deliverables complete
Why At Risk, Not Off Track
• GenAI grounding risk (R-13) escalated from the Week 2 brief — needs Week 3 refinement
• DA → DS hand-off (DEP-01) timing is tight and could compress Week 3 integration
• Neither issue is critical yet, but both require active management in Week 3
FinTrust Digital Bank — Week 2 PM Status Deck | Lamiaa SAMRAOUI | 2

## Slide 3
Week 2 Completed
All 7 PM-owned deliverables finished on schedule
✅ Progress Tracker
✅ Updated Four-Week Timeline
✅ Risk Register (13 risks)
✅ Issue Log (6 issues)
✅ Dependency Register (8 dependencies)
✅ Decision Log (6 decisions)
✅ Week 2 Status Report
FinTrust Digital Bank — Week 2 PM Status Deck | Lamiaa SAMRAOUI | 3

## Slide 4
Active Risks & Issues
Key items requiring Week 3 attention
ID | Item | Priority
R-05 / R-13 | GenAI grounding risk — escalated per Week 2 brief | High
R-02 / R-08 | Track schedule slippage / limited buffer | High
R-12 | DA → DS hand-off timing pressure | Medium
R-09 | DS/MLE integration format not yet agreed | Medium
Issue | Cross-track visibility not available in Week 2 | By design
FinTrust Digital Bank — Week 2 PM Status Deck | Lamiaa SAMRAOUI | 4

## Slide 5
Key Decisions
Six decisions logged in Week 2, each backed by evidence
1
Prioritise DEP-01 (DA → DS) as the Week 2 critical path
2
Adopt a labelled-assumption approach for cross-track monitoring
3
Split the Risk Register into two tables for readability
4
Add R-12 — DA → DS timing risk, evidenced by the Week 2 roadmap
5
Add R-13 — GenAI grounding risk, evidenced by the Week 2 brief
6
Keep Week 2 monitoring notes separate from Week 1 registers
FinTrust Digital Bank — Week 2 PM Status Deck | Lamiaa SAMRAOUI | 5

## Slide 6
Week 3 Priorities
Focus areas as formal collaboration begins
🎯
Confirm DA → DS hand-off completion and validate Week 2 assumptions
🎯
Coordinate the DS → MLE hand-off (DEP-02)
🎯
Monitor GenAI grounding refinement and re-testing (R-13 mitigation)
🎯
Establish format/interface agreements between DS and MLE (R-09 mitigation)
🎯
Update all governance documents with confirmed Week 2 data
🎯
Prepare for end-to-end testing in Week 4
FinTrust Digital Bank — Week 2 PM Status Deck | Lamiaa SAMRAOUI | 6