## Final_Deliverable_Tracker
Track | Required Output | Status | Complete? | Outstanding Work
Data Analytics | Dashboard and Analysis | Confirmed Partial (SQL complete; Python and dashboard in progress) | Partially | Python analysis, Power BI dashboard, findings write-up
Data Science | Final Model | Reviewed (public GitHub repository and two public LinkedIn posts from two additional DS contributors) | Yes (unvalidated) | Integration readiness confirmation
ML Engineering | Final Workflow | Confirmed (direct Slack communication from Dineo Nadine Sithole) | Yes (pipeline and API functional; model quality limited) | Model refinement beyond current recall
Generative AI | Final Assistant | Not Confirmed | No evidence available | All information
Project Management | Final Documentation | Complete | Yes | None

## Integration_Readiness
Track | Contributor | Main Output | Evidence Type | Evidence Level | Integration Readiness | Outstanding Work
Data Analytics | Franklin | Advanced SQL complete; Python and Power BI in progress | Direct message | Confirmed | Partially Ready | Python analysis and Power BI dashboard
Data Analytics | Mohammed Rashid | Documentation and dashboard screenshot | Direct DM and shared file | Confirmed | Partially Ready | Python analysis, Power BI dashboard, findings write-up
Data Science | Unotidashe Jacob Hove, Emmanuel Asamoah Oppong, Emmanuella Arhin | Model validated; code on GitHub; Week 4 posts confirm testing, validation, calibration | Public GitHub and LinkedIn posts | Reviewed | Not Confirmed | Integration readiness confirmation
ML Engineering | Dineo Nadine Sithole | Working pipeline and API; model metrics documented; bugs found and fixed | Direct Slack message | Confirmed | Partial (pipeline and API functional; model quality limited) | Model refinement beyond current recall
ML Engineering (alternative) | Charlez023 | Full repository: code, 20 tests, FastAPI endpoint | Public GitHub repository | Reviewed | Not Confirmed | Integration readiness confirmation
Generative AI | No contributor identified | Not available | No source | Not Confirmed | Not Confirmed | All information
Project Management | Lamiaa SAMRAOUI | All PM deliverables Weeks 1 to 4 | This submission | Confirmed | Ready | None

## Risk_Register_Final
ID | Risk | Probability | Impact | Final Status
R-01 | Data-quality issues | Not specified | Not specified | Closed
R-02 | Track schedule slippage | Not specified | Not specified | Closed
R-03 | Dependency communication | Not specified | Not specified | Closed
R-04 | Predictive model limited by imbalance | Medium | High | Accepted (confirmed by MLE metrics)
R-05 | GenAI hallucination | Not specified | Not specified | Open
R-06 | Scope creep | Not specified | Not specified | Closed
R-07 | Tool access | Not specified | Not specified | Closed
R-08 | Limited buffer | Not specified | Not specified | Closed
R-09 | Integration fails due to incompatible outputs | Medium | High | Accepted
R-10 | Inconsistent documentation | Not specified | Not specified | Closed
R-11 | Unclear acceptance criteria | Not specified | Not specified | Closed
R-12 | DA to DS hand-off timing | Not specified | Not specified | Closed
R-13 | GenAI grounding failures | High | High | Open
R-14 | Week 4 time compression | Not specified | Not specified | Closed
R-15 | Cross-track integration readiness not confirmed | High | Medium | Accepted

## Issue_Log_Final
Issue | Impact | Priority | Final Status
Cross-track integration readiness not confirmed for most tracks | Cannot fully validate integration | High | Accepted
Generative AI evidence not available | R-13 status not updatable | Medium | Open
ML Engineering model quality limited (recall 0.04) | Predictions not production-ready | High | Accepted
Two ML Engineering sources exist | Both documented | Low | Closed
Multiple contributors per track | Per-contributor tracking applied | Medium | Closed

## Decision_Log_Final
Decision | Reason | Evidence | Impact | Date
Adopted four-level evidence hierarchy | Distinguish confirmation levels | Weeks 3 and 4 briefs | Clear labels throughout | Week 3, Day 1
Documented each contributor separately | Multiple independent contributors per track | Direct communication and shared files | Per-contributor accuracy | Week 3, Day 1
Upgraded MLE to Confirmed | Direct Slack communication from Dineo Nadine Sithole | Detailed pipeline status and metrics | MLE is Confirmed at Partial readiness | Week 4, Day 1
Documented MLE model quality limitation | Recall on risk class is 0.04 | Dineo's Slack message | Honest reporting of model limits | Week 4, Day 1
Upgraded DA to Confirmed | Direct DM and documentation from Mohammed Rashid and Franklin | Dashboard screenshot and message | DA is Confirmed at Partial readiness | Week 4, Day 1
Closed 10 risks as Resolved | No further issues | Week 4 review | Clean final register | Week 4, Day 2
Accepted R-04, R-09, R-15 | Fundamental limitations cannot be resolved in scope | Documented rationale | Honest final state | Week 4, Day 2
Added two additional Data Science public LinkedIn sources | Multiple Week 4 DS posts available; strengthens evidence base | Emmanuel Asamoah Oppong and Emmanuella Arhin LinkedIn posts | DS evidence now from three independent contributors | Week 4, Day 3

## Timeline_Status
Week | Phase | Status
Week 1 | Understand and Plan | Complete
Week 2 | Analyse and Prepare | Complete
Week 3 | Develop and Integrate | Complete
Week 4 | Test, Refine and Present | Complete

## Evidence_Sources
Track | Contributor | Evidence Type | Evidence Description | Evidence Level
Data Analytics | Franklin | Direct message | SQL complete; Python and Power BI expansion in progress; no blockers | Confirmed
Data Analytics | Mohammed Rashid | Direct LinkedIn DM | Direct message confirming documentation and progress | Confirmed
Data Analytics | Mohammed Rashid | Shared file (screenshot) | Dashboard screenshot: customer KPIs, transaction value, success rate, risk review rate, channel and segment distribution, high-value transactions | Confirmed
Data Science | Unotidashe Jacob Hove | Public GitHub repository | Model validated; code on GitHub; reviewed by PM | Reviewed
Data Science | Emmanuel Asamoah Oppong | LinkedIn post | Week 4 data quality audit, KPI reconciliation, five recommendations; At Risk segment is 40 percent of customers and 34.8 percent of transaction value | Reviewed
Data Science | Emmanuella Arhin | LinkedIn post | Week 4 ML model testing; 20 feature variations, 8 models compared, calibration improved from 0.28 to 0.02, ROC-AUC 0.68 | Reviewed
ML Engineering | Dineo Nadine Sithole | Direct Slack message | Pipeline and API status, model metrics (recall 0.04), two bugs found and fixed | Confirmed
ML Engineering (alternative) | Charlez023 | Public GitHub repository | Full repository: code, 20 tests, FastAPI endpoint; reviewed by PM | Reviewed
Generative AI | No contributor identified | No source | No evidence available | Not Confirmed
Project Management | Lamiaa SAMRAOUI | This submission | All PM deliverables Weeks 1 to 4 | Confirmed